## Priority ladder
# | Action | Cost | Impact | Effort | Why this order
1 | Per-profile Open Graph cards | $0 | Highest | 2-3 hrs | Every share becomes free marketing. Single biggest lever.
2 | robots.txt + sitemap.ts + canonical URLs | $0 | Highest | 1 hr | Nothing else SEO matters until Google can crawl + dedupe.
3 | Google Search Console + Bing | $0 | High | 30 min | Free ranking data + alerts. Foundation for all SEO loops.
4 | Schema.org JSON-LD (Org + WebSite + SoftwareApp) | $0 | High | 1 hr | Drives knowledge panel + rich results.
5 | GA4 + 5 named conversions | $0 | High | 1 hr | Without attribution, every channel choice is a guess.
6 | Claim all social handles + identical bios | $0 | Medium | 2 hrs | Cheap insurance against impersonation; cross-platform recs.
7 | Microsoft Store PWA + Google Play TWA | $25 once | Medium | 1-2 hrs | Two store listings nearly free.
8 | Public-profile opt-in + programmatic SEO | $0 | Highest (compounds) | 1 day | Each public profile = indexable page. 5k profiles = 5k pages.
9 | Blog + 4-article cluster launch | $0 | Highest (compounds) | 1-2 wks | Owns 'dating for creatives' SERPs before competitors notice.
10 | Resend lifecycle emails (welcome + reengagement) | $0 (then $20/mo) | High | 1 wk | Recovers paid subscribers from churn. Free at first.
11 | Influencer outreach (trade premium for posts) | $0 cash | High | Ongoing | Solo founder advantage. VCs can't do this credibly.
12 | Product Hunt launch | $0 | High (one shot) | 4 wks prep | 3-5k visitors in one day if executed. Plan ruthlessly.
13 | First paid ad test (Reddit, $10/day) | $300/mo | Medium | 2 hrs setup | Cheaper CPMs than Meta. Niche audience match.
14 | Meta + TikTok boosts on org. winners | $1200/mo | Medium-High | Ongoing | Only after organic signal is real. Boost winners, not cold creative.
15 | iOS Capacitor build | $99/yr + 2-4 wks | Medium | Big lift | Only after 1k+ web users — Apple reviews are brutal on thin DAU.

## Free (no $)
Wave | Category | Action | Time cost | Why it matters | Done?
1 | Technical SEO | Create /public/robots.txt | 5 min | Tells crawlers what to index. One-line file.
1 | Technical SEO | Build app/sitemap.ts (Next 16 convention) | 30 min | Lets Google find every public page automatically.
1 | Technical SEO | Add canonical URLs via metadata API | 20 min | Prevents www/non-www duplicate-content penalties.
1 | Technical SEO | Force www redirect in next.config.ts | 10 min | One host = clean SEO juice, no DNS surprises.
1 | Technical SEO | Confirm HTTPS everywhere (Vercel handles) | 5 min | Required for trust + Google rankings.
1 | Technical SEO | PageSpeed audit + fix below-90 mobile scores | 1-3 hrs | Core Web Vitals = ranking factor.
1 | Open Graph | Audit existing app/opengraph-image.tsx renders | 15 min | Default share card across all generic links.
1 | Open Graph | Build app/profile/[username]/opengraph-image.tsx | 2-3 hrs | BIGGEST single lever — every share = free marketing.
1 | Open Graph | Add twitter card metadata to root layout | 15 min | Wide hero card instead of tiny thumbnail on X.
1 | Open Graph | Validate via opengraph.xyz, Twitter Card Validator | 15 min | Catches broken cards before users see them.
1 | Search Console | Verify mitypeapp.com via DNS | 20 min | Free Google index data + alerts.
1 | Search Console | Submit sitemap.xml | 2 min | Speeds up indexing dramatically.
1 | Search Console | Run URL Inspection on homepage + 1 profile | 10 min | Catches client-side rendering blocks.
1 | Search Console | Set US international targeting | 2 min | Prioritizes US results.
1 | Search Console | Wire up email alerts | 5 min | Free monitoring for indexing/security issues.
1 | Bing Webmaster | Add site (import from Google) | 5 min | Bing + DuckDuckGo + ChatGPT search coverage.
1 | Schema.org | Add Organization JSON-LD | 30 min | Drives Google knowledge panel for 'mitype' searches.
1 | Schema.org | Add WebSite + SearchAction JSON-LD | 20 min | Embeds search box in Google results.
1 | Schema.org | Add SoftwareApplication JSON-LD | 20 min | Lets Google show install/launch CTAs.
1 | Schema.org | Add Person JSON-LD on opt-in profile pages | 1 hr | Each public profile becomes a rich result.
1 | Analytics | Install GA4 with strategy=afterInteractive | 30 min | Free, deep funnel data.
1 | Analytics | Configure 5 conversion events (signup, profile, match, msg, sub) | 20 min | Without these, channel attribution is impossible.
1 | Analytics | Install Vercel Analytics or Plausible (free tier) | 10 min | Daily glance dashboard.
1 | Analytics | Build canonical UTM tag spreadsheet + tag every link | 1 hr | Untagged traffic = black hole.
1 | Analytics | Add referral_source column to profiles table | 30 min | Stripe → signup attribution loop.
2 | Social handles | Claim @mitype, @mitypeapp, @getmitype on IG/TikTok/X/LinkedIn/YouTube/Threads/Bluesky | 2 hrs | Prevents impersonation; buys optionality.
2 | Social handles | Set identical bio + link across all platforms | 30 min | Algorithms recommend you to each other's users.
2 | App stores | Submit PWA to Microsoft Store via PWA Builder | 1 hr | Free store listing from your existing manifest.
2 | Social content | Batch-shoot Sunday TikTok/Reels content | 2-3 hrs/wk | 5-7 short videos/wk, organic reach engine.
2 | Social content | Cross-post TikTok → YouTube Shorts | 5 min/post | Free distribution; old vids earn forever.
2 | Social content | 1-2 X posts/day + reply to bigger accounts | 20 min/day | Indie hacker + tech press lurk here.
2 | Social content | 1 LinkedIn long post/week | 30 min/wk | Press + investors lurk here.
2 | Reddit | Comment on 5+ posts/wk in target subs (no promo) | 20 min/day | Mods sniff drive-by promo from orbit.
2 | Reddit | Post to weekly r/SideProject / r/IndieDev show-off threads | 30 min/wk | Allowed self-promo; high quality traffic.
2 | Discord | Become active in 3-4 creative discords | 30 min/day | Most allow self-promo for active members.
2 | Product Hunt | Build hunter list of 50+ committed upvoters | 1-2 wks | First 4 hours determine the day.
2 | Product Hunt | Prepare assets (30s demo, 6 images, tagline) | 1-2 days | Required for a credible launch.
2 | Product Hunt | Launch day: respond within 5 min for first 6 hrs | Full day | Highest-ROI day of the year if executed.
3 | Content/SEO | Set up /blog as subpath of mitypeapp.com | 2-3 hrs | Subpath > subdomain for SEO juice.
3 | Content/SEO | Publish 1 article/wk in topic clusters (1500-2500 words) | 4-6 hrs/wk | Owns 'dating for creatives' SERP cluster.
3 | Content/SEO | Internal-link 3+ articles + 2 product pages per post | Per article | How Google figures out what's important.
3 | Programmatic SEO | Add 'public profile' opt-in toggle | 2 hrs | Each public profile = indexable page.
3 | Programmatic SEO | Server-render public profiles with full schema markup | 3-4 hrs | Required for Google to see them.
3 | Programmatic SEO | Build /discover/[city] and /discover/[category] index pages | 1 day | Pure programmatic SEO surface.
3 | Programmatic SEO | Submit new public profiles via IndexNow API | 2 hrs | Faster Bing/Yandex indexing, free.
3 | Press/PR | Pitch Indie Hackers, Lenny's Newsletter, niche press | Ongoing | Free, high-quality readership.
3 | Press/PR | Submit Show HN once when product is genuinely good | 2 hrs prep | One shot — pick Tuesday AM Pacific.
3 | Press/PR | Pitch It's Nice That, AIGA, PetaPixel, Designer News | 1 hr/pitch | Smaller readership but exactly your people.
3 | Influencers | Build 100-prospect outreach spreadsheet | 1 day | 10 DMs/day target.
3 | Influencers | DM Tier 1 (50k+) lifetime premium + creator badge | 20 min/DM | Trade access for reach. No cash.
3 | Influencers | DM Tier 2 (5-50k) 6 months free + early access | 20 min/DM | Best per-dollar conversion tier.
3 | Influencers | Stand up 'first 100 creators' program | 1 wk | Superusers who become evangelists.
3 | Backlinks | Submit to Crunchbase, AngelList, BetaList, F6S, AppAdvice | 2 hrs | Free authoritative directory backlinks.
3 | Backlinks | HARO / Help A B2B Writer responses | 30 min/day | Get quoted in major publications free.
3 | Backlinks | Pitch 3 podcast appearances | Ongoing | Show notes backlink + audience exposure.
4 | Trust signals | Add /safety page (verification, harassment, reporting) | 3-4 hrs | Press hook + Google trust factor.
4 | Trust signals | Add /about page with founder bio + photo | 2 hrs | Faceless apps look like scams; one face fixes it.
4 | Trust signals | Link Privacy + Terms in footer of every page | 30 min | Trust signal + legal protection.
4 | Trust signals | Add testimonial section to homepage (3-5 quotes) | 2 hrs | Social proof above the fold.
4 | Trust signals | Add 'As seen in [logo]' strip after first press hit | 1 hr | Even one logo doubles trust.
4 | Reviews | Build in-product 'how's it going?' prompt at 30 days + 1 match | 3 hrs | Highest-ROI testimonial source you can build.
4 | Reviews | Pipe positive responses to /testimonials page | 2 hrs | Living social proof.
4 | Reviews | Submit to Trustpilot (free listing) | 30 min | Reviews show in Google rich results.
4 | Reviews | Submit to G2/Capterra at 1k+ users | 1 hr | Surface in B2B-adjacent queries.
4 | Reviews | Submit to top-5-ranking 'best dating app' listicles | Ongoing | Some free, some paid (only pay top-5).
4 | Brand | Quarterly brand audit: logo/tagline/color/voice consistency | 2 hrs/qtr | Brand = same thing in 10 places.
4 | Metrics | Monthly dashboard review (1st Mon of month) | 30 min/mo | Catches drift before it compounds.

## Paid ($)
Wave | Category | Action | Cost type | Setup ($) | Monthly ($) | When to spend | Notes | Done?
2 | App stores | Google Play TWA via PWA Builder | One-time | 25 | 0 | Wave 2 (this month) | Play Console developer fee. Lifetime.
2 | App stores | Apple Developer Program | Annual | 0 | 0 | After 1k+ web users | $99/yr — only if doing iOS Capacitor build.
3 | App stores | iOS Capacitor build (contractor or self) | One-time | 0 | 0 | Q3-Q4 | $0 if DIY (~2-4 wks); $3-5k if contracted.
3 | Email | Resend (free tier covers <3k emails/mo) | Free → paid at scale | 0 | 0 | Wave 2 | Free for first 3,000/mo, then $20/mo for 50k.
3 | Email | Resend Pro (50k emails/mo) | Monthly | 0 | 20 | When >3k/mo | Tier scales linearly with volume.
3 | Press tooling | Press release distribution (PR Newswire / EIN) | Per release | 350 | 0 | Only on real news | Skip until 100k+ users milestone.
3 | Backlinks | Sponsor small creative newsletter (1 slot/mo) | Monthly | 0 | 200 | Month 3+ | $100-300/sponsorship; pick newsletters w/ backlink.
3 | Paid ads | Meta (Instagram + Facebook) test | Monthly | 0 | 600 | After 500-1k organic signups | $20/day. Boost top-performing organic Reels.
3 | Paid ads | TikTok Ads (boost organic winners) | Monthly | 0 | 600 | After 50k+ org. video views | $20/day. Never run cold creative on TikTok.
3 | Paid ads | Reddit Ads | Monthly | 0 | 300 | Month 3+ | $10/day. r/photography, r/Design, r/illustrators.
3 | Paid ads | Google Search (long-tail only) | Monthly | 0 | 900 | Month 3+ | $30/day cap. Avoid 'dating app' head term.
4 | Reviews | Trustpilot (paid tier for invitations) | Monthly | 0 | 250 | After 500+ subs | Free listing exists; paid adds invitation flow.
4 | Reviews | Premium directory listing (paid 'best of' lists) | Per listing | 200 | 0 | Only if site ranks top-5 in Google | Skip pay-for-placement scams.
4 | SEO tools | Ahrefs / Semrush (Lite plan) | Monthly | 0 | 130 | Month 3+ | Optional — free Search Console covers 80%.
4 | SEO tools | Ubersuggest (cheaper alternative) | Monthly | 0 | 30 | Month 3+ | Lite-touch keyword research.
1 | Infrastructure | Vercel Pro (when bandwidth needed) | Monthly | 0 | 20 | Now or at scale | Free tier covers ~100GB/mo.
1 | Infrastructure | Supabase Pro (when free tier maxes) | Monthly | 0 | 25 | At ~5k MAU | Free tier covers small launches.
1 | Infrastructure | Sentry Team | Monthly | 0 | 26 | Now (already on) | 5k errors/mo + perf monitoring.
1 | Infrastructure | Domain (mitypeapp.com) | Annual | 0 | 1 | Now (already paid) | ~$12-15/yr typical.
|  | TOTALS |  | 575 | 3102

## Phased budget
Phase | Description | Setup ($) | Monthly ($) | Annualized ($) | Notes
Week 1 (foundation) | All free items above. Domain already paid. | 0 | 0 | 0 | Foundation is $0 cash.
Month 1 (launch) | Google Play TWA fee only. | 25 | 0 | 25 | $25 one-time. Everything else free.
Month 2-3 (lifecycle) | Resend free tier (<3k/mo emails). | 0 | 0 | 0 | Email still free at this volume.
Month 3+ (growth) | Email Pro + Reddit Ads small test. | 0 | 320 | 3840 | $20 Resend + $300 Reddit.
Month 4+ (paid acq.) | Add Meta + TikTok boosts (after org. signal). | 0 | 1520 | 18240 | $320 + $600 Meta + $600 TikTok.
Month 6+ (full stack) | Add Google Search + 1 newsletter sponsor. | 0 | 2620 | 31440 | $1520 + $900 Google + $200 sponsor.
Month 12+ (scale) | Add Apple Dev + iOS build + Trustpilot. | 100 | 2870 | 34540 | $99 Apple + $250 Trustpilot.